## TimelineExcel
Row ID | Swimlane | Sub-swimlane | Milestone/Task Title | Description | Start date | End date | % Complete | Owner | Depends on | Notes | Updates | Item Type | Label Position | Milestone Shape | Bar Style | Milestone Row | Shown | Color Category | Title Color | Health
1 | Product |  | Discovery and requirements | Customer interviews and a journey map, ending in the requirements the build starts from | 2026-10-01 | 2026-11-30 | 100 | Product team |  | **Scope:** customer interviews and a journey map |  | Phase
2 | Product |  | Requirements sign-off |  |  | 2026-11-30 |  | Sponsor |  |  |  | Milestone
3 | Engineering | Backend | API build |  | 2026-11-01 | 2027-02-28 | 40 | Backend team |  | Item Type left blank: Lanetrace reads the dates and draws a Phase. | [10/03/2026 9:30 AM] Auth service is two weeks behind, so Health is At Risk | [8 empty] | At Risk
4 | Engineering | Frontend | Portal UI |  | 2026-12-01 | 2027-02-28 | 15 | Frontend team | 2, 5 |  |  | Task | Auto |  | Flat
5 | Engineering |  | Architecture review |  |  | 2026-11-15 |  | Tech lead |  | Go or no-go on the hosting design |  | Decision
6 | Marketing |  | Launch announcement |  |  | 2027-03-10 |  | Marketing |  |  |  | Event | Above
7 | Operations |  | Go-live |  |  | 2027-03-31 |  | Program office | 3, 4 |  |  | Milestone |  | flag |  |  |  | #E2A32D
8 | Operations |  | Legacy decommission |  | 2027-04-01 | 2027-05-31 | 0 | Operations | 7 | Shown is No, so this row stays out of the timeline until you change it. |  | Phase |  |  |  |  | No

## Instructions
Lanetrace data template
Fill in the TimelineExcel sheet, save the file, and drop it on Lanetrace. This sheet explains every column and rule.
Quick start
1 | Replace the sample rows on the TimelineExcel sheet with your own items. Keep the header row exactly as it is: Lanetrace finds columns by their header text.
2 | Give every row a Swimlane, a Milestone/Task Title and an End date. Blue headers mark the required columns.
3 | Leave Start date blank for a milestone, event or decision. Fill it in for a task or phase.
4 | Save the file as .xlsx. Keep the sheet name TimelineExcel.
5 | In Lanetrace, drag the file onto the page, or open Settings and choose Load .xlsx. Lanetrace lists any missing columns or skipped rows when it loads.
Columns
Tip | Select any cell on the TimelineExcel sheet to see a short hint for that column. Columns with a fixed set of values have a dropdown.
Column | Required | Accepts | What it does | Example
Row ID | Required | Number or short code | Identifies the row. Keep it the same between versions of the file. | 12 or ENG-004
Swimlane | Required | Text, up to 30 characters | Top-level group, like a team or workstream. Each new name becomes a swimlane. | Engineering
Sub-swimlane | Optional | Text, up to 30 characters | Optional second level inside a swimlane. Blank keeps the item in the main row. | Backend
Milestone/Task Title | Required | Text, up to 100 characters | The label on the timeline. | API build
Description | Optional | Text | What the item covers: scope, deliverables, definition of done. Shows under the title in the tooltip and item form. | Configure surveys for 22 service lines
Start date | Optional | Date | First day of a task or phase. Leave blank for a milestone, event or decision. | 2026-11-02
End date | Required | Date | Last day of a task or phase, or the date of a milestone, event or decision. The bar includes this day. | 2027-01-29
% Complete | Optional | Whole number 0 to 100 | Progress. Fills the bar from the left. Blank counts as 0. | 40
Owner | Optional | Text | Person or team responsible. Shows in the tooltip and the status update. | Backend team
Depends on | Optional | Row IDs, separated by commas | Items that must finish before this one starts. Lanetrace flags any item that starts before a predecessor finishes. | 3, 5
Notes | Optional | Text with basic Markdown | Detail for the tooltip and item panel. Supports **bold**, *italic*, # headings, - bullets and 1. numbered lists. | **Scope:** login, profile
Updates | Optional | Dated entries, newest first | Running status log. Lanetrace adds each new update to the top with its date and time. One entry per line, starting with the stamp in brackets. | [10/29/2026 2:05 PM] Vendor confirmed the SFTP account
Item Type | Optional | Task, Phase, Milestone, Event, Decision | What to draw. Blank lets Lanetrace decide from the dates (see How Lanetrace reads your data). | Phase
Label Position | Optional | Auto, Above, Below, Left, Right, Inside | Where the title sits. Auto puts it inside the bar when it fits, otherwise beside it. | Auto
Milestone Shape | Optional | diamond, diamond-tall, circle, triangle-right, triangle-down, triangle-down-large, star, flag | Marker shape for a milestone, event or decision. Blank uses the type default. | flag
Bar Style | Optional | Flat, Chevron, Pill | Bar ends for a task or phase. Blank gives tasks a chevron and phases rounded ends. | Flat
Milestone Row | Optional | Whole number 1 to 6 | Moves a milestone, event or decision out of its swimlane into that row of the strip above the timescale, with the Lanetrace setting Milestones: As set per item (the default). Blank keeps it in its swimlane. | 2
Shown | Optional | Yes or No | No hides the item without deleting it. Blank shows it. | No
Color Category | Optional | Hex color | Overrides the swimlane color for this one item. | #E2A32D
Title Color | Optional | Auto, White, Dark or a hex color | Auto picks white or dark text for contrast. Set it only to override. | Auto
Health | Optional | On Track, At Risk, Off Track | Your read on the item. Blank is Auto: Lanetrace works it out from the dates and % complete. Green, Amber and Red also work. | At Risk
Item types
Type | Dates | Draws as | Use it for | Default shape
Task | Start and end | Bar with a pointed end | A piece of work with one owner, usually shorter than a quarter. | Chevron bar
Phase | Start and end | Bar with rounded ends | A stage of the work that holds several tasks, like Discovery or Build. | Pill bar
Milestone | End date only | Marker on one day | A checkpoint or deliverable: sign-off, go-live, release. | Diamond
Event | End date only | Marker on one day | Something outside the work that affects it: an audit, a conference, a freeze window. | Triangle
Decision | End date only | Marker on one day | A point where someone chooses a path: go or no-go, vendor selection. | Star
How Lanetrace reads your data
Item Type left blank | No start date, or a start and end on the same day, makes a Milestone. 92 days or less makes a Task. Longer makes a Phase. Set Item Type to Task to draw a one-day bar.
Dates | Use real Excel dates. Text dates work as 2026-03-31 or 3/31/2026. Day-first text such as 31/03/2026, impossible dates such as 2026-02-30, and words such as TBD are not drawn. Lanetrace lists them in its "needs attention" chip.
% Complete | Whole numbers from 0 to 100. Cells formatted as Excel percentages (0.5 shown as 50%) also work when the whole column uses that format. Values above 100 count as 100.
Shown | No, N, Off, Hidden, FALSE or 0 hides the row. Anything else, or blank, shows it.
Headers | Lanetrace matches columns by header text; capitals do not matter. A renamed header is ignored, and the load message names the missing required columns. Extra columns of your own are fine.
CSV | A CSV file with these same headers loads the same way, for example a CSV UTF-8 saved from Excel. Commas, semicolons or tabs all work.
Depends on | List the Row IDs of items that must finish before this one starts. Lanetrace flags an item that starts before a predecessor finishes, an ID that matches no row, and a chain that loops back on itself. It never moves your dates.
Row ID | Edits you make inside Lanetrace stay attached to their rows across new versions of this file. Keep Row IDs, titles and swimlanes stable between versions.
Colors | Swimlane colors come from the theme you pick in Lanetrace. Use Color Category only to call out a single item.
Glossary
Swimlane | A horizontal band that groups related items, usually a team, workstream or product area.
Sub-swimlane | A labeled row inside a swimlane, used to split a team into groups such as Backend and Frontend.
Item | Any one row of this sheet: a task, phase, milestone, event or decision.
Summary bar | What a collapsed swimlane shows in Lanetrace: one bar from its earliest to its latest date, with the item count and % complete weighted by duration.
Milestone strip | A band above the timescale for milestones, events and decisions. Fill in Milestone Row to move one item there, or move them all in Settings > Timeline.
Today marker | The red line on the current date. Settings > Timeline can pin it to a custom "as of" date for status reports.
Load messages and fixes
Message |  | What it means | Fix
Sheet "TimelineExcel" not found |  | The data sheet was renamed. | Rename the data sheet back to TimelineExcel.
Missing column |  | A required header was renamed or deleted. | Copy the header row from a fresh template.
Skipped rows with no title |  | Those rows have data but no Milestone/Task Title. | Add a title, or delete the rows.
Date not recognized |  | A date cell holds text Lanetrace cannot read. | Enter a real date, or use the form 2026-03-31.
Needs a start and end date |  | A Task or Phase is missing one of its dates. | Add the missing date, or clear Item Type so Lanetrace infers it.
End date is before the start date |  | The two dates are reversed. | Swap them. Lanetrace draws the bar anyway and flags it.
Starts before "…" finishes |  | The item starts before an item in its Depends on column finishes. | Move the start date, or remove the Row ID from Depends on.
Depends on Row ID … which does not exist |  | Depends on names a Row ID that no row has. | Fix the ID, or remove it.
Circular dependency |  | Items depend on each other in a loop. | Remove one Row ID from the loop.
Template for Lanetrace v4.16.0. Created 2026-10-29. Sample dates start in the current month.